## Weekly_Schedule_Tasks
| 2018-08-12 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-18 | 2018-08-19 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-25 | 2018-08-26 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-09-01 | 2018-09-02 | 2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07
Projects
IOT-Smart Parking Project | 2018-08-15: Follow up with Kevin for POC; 2018-08-17: Get the task list uploaded on Github; 2018-08-19: Talk to city of Bellevue for POC
IOT-Smart Parking Project | 2018-08-16: Start the IOT sensor Research; 2018-08-17: Start the IOT sensor Research; 2018-08-18: Start the IOT sensor Research; 2018-08-19: Start the IOT sensor Research; 2018-08-20: Start the IOT sensor Research; 2018-08-21: Start the IOT sensor Research; 2018-08-22: Start the IOT sensor Research; 2018-08-23: Start the IOT sensor Research; 2018-08-24: Start the IOT sensor Research; 2018-08-25: Start the IOT sensor Research
IOT-Smart Parking Project | 2018-08-16: Find a suitable Technology to work with IOT Data; 2018-08-17: Find a suitable Technology to work with IOT Data; 2018-08-18: Find a suitable Technology to work with IOT Data; 2018-08-19: Find a suitable Technology to work with IOT Data; 2018-08-20: Find a suitable Technology to work with IOT Data; 2018-08-21: Find a suitable Technology to work with IOT Data; 2018-08-22: Find a suitable Technology to work with IOT Data; 2018-08-23: Find a suitable Technology to work with IOT Data; 2018-08-24: Find a suitable Technology to work with IOT Data; 2018-08-25: Find a suitable Technology to work with IOT Data
IOT-Smart Parking Project | 2018-08-17: Come up with an installation strategy for the IOT sensor; 2018-08-18: Come up with an installation strategy for the IOT sensor; 2018-08-19: Come up with an installation strategy for the IOT sensor; 2018-08-20: Come up with an installation strategy for the IOT sensor; 2018-08-21: Come up with an installation strategy for the IOT sensor; 2018-08-22: Come up with an installation strategy for the IOT sensor; 2018-08-23: Come up with an installation strategy for the IOT sensor; 2018-08-24: Come up with an installation strategy for the IOT sensor; 2018-08-25: Come up with an installation strategy for the IOT sensor
IOT-Smart Parking Project | 2018-08-17: Send Pruthvi and Anil IOTA information and EDGE and Particle Technology; 2018-08-23: Get the use case document/sensor/evaluation template completed
IOT-Smart Parking Project
Weekly meetings | 2018-08-18: Have weekly call for the team; 2018-08-23: Get with Pruthvi to help with CMA; 2018-08-26: Have weekly call for the team
Real Estate | 2018-08-17: Come up with Proposal and RFP Template; 2018-08-18: Come up with Proposal and RFP Template; 2018-08-19: Come up with Proposal and RFP Template; 2018-08-20: Come up with Proposal and RFP Template; 2018-08-21: Come up with Proposal and RFP Template; 2018-08-22: Come up with Proposal and RFP Template; 2018-08-23: Come up with Proposal and RFP Template; 2018-08-24: Come up with Proposal and RFP Template; 2018-08-25: Come up with Proposal and RFP Template; 2018-08-26: Come up with Proposal and RFP Template
Real Estate | 2018-08-16: Get the CMA steps deck completed; 2018-08-17: Start the CMA automation and machine learning algorithm; 2018-08-18: Start the CMA automation and machine learning algorithm; 2018-08-19: Start the CMA automation and machine learning algorithm; 2018-08-20: Start the CMA automation and machine learning algorithm; 2018-08-21: Start the CMA automation and machine learning algorithm; 2018-08-22: Start the CMA automation and machine learning algorithm; 2018-08-23: Start the CMA automation and machine learning algorithm; 2018-08-24: Start the CMA automation and machine learning algorithm; 2018-08-25: Start the CMA automation and machine learning algorithm; 2018-08-26: Start the CMA automation and machine learning algorithm
Real Estate
Real Estate
Real Estate
Real Estate
AE&C inc work | 2018-08-16: Get the deck and website started; 2018-08-17: Get the deck and website started; 2018-08-18: Get the deck and website started; 2018-08-19: Get the deck and website started; 2018-08-20: Get the deck and website started; 2018-08-21: Get the deck and website started; 2018-08-22: Get the deck and website started; 2018-08-23: Get the deck and website started; 2018-08-24: Get the deck and website started; 2018-08-25: Get the deck and website started
AE&C inc work
AE&C inc work
AE&C inc work
AE&C inc work
AE&C inc work
Note on F4: Vishwambhara Adiga: Completed and follow up next week if you don’t hear back
Note on H4: Vishwambhara Adiga: Done. Anil and Pruthvi to get accounts
Note on J4: Vishwambhara Adiga: Done. Follow up with Kevin on Permits
Note on G5: Anil: In Progress
Note on H5: Anil: In Progress
Note on I5: Anil: In Progress
Note on J5: Anil: In Progress
Note on K5: Anil: In Progress
Note on L5: Anil: In progress
Note on M5: Anil: In progress
Note on N5: Anil: In progress
Note on O5: Anil: In progress
Note on P5: Anil: In progress
Note on G6: Pruthvi: In Progress
Note on H6: Pruthvi: In Progress
Note on I6: Pruthvi: In Progress
Note on J6: Pruthvi: In Progress
Note on K6: Pruthvi: In Progress
Note on L6: Pruthvi: In Progress
Note on M6: Pruthvi: In Progress
Note on N6: Pruthvi: In Progress
Note on O6: Pruthvi: In Progress
Note on P6: Pruthvi: In Progress
Note on H8: Vishwambhara Adiga: Done.
Note on N8: Vishwambhara Adiga: In progress
Note on I10: Vishwambhara Adiga: Fix a time
Note on N10: Vishwambhara Adiga:
Note on Q10: Vishwambhara Adiga: Fix a time
Note on H11: Vishwambhara Adiga: Not Started Yet
Note on G12: Vishwambhara Adiga: ppt done, integrating with Microstrtegy. Anil to help Pruthvi as required
Note on H12: Pruthvi: In work
Note on I12: Pruthvi: In work
Note on J12: Pruthvi: In work
Note on K12: Pruthvi: In work
Note on L12: Pruthvi: In work
Note on M12: Pruthvi: In work
Note on N12: Pruthvi: In work
Note on O12: Pruthvi: In work
Note on P12: Pruthvi: In Progress
Note on Q12: Pruthvi: In work